## TimeLog
			51.25	28.75	30	88.5
TIME LOG

Date	Time Start	Time End	Funk Time (hours)	Jorge Time (hours)	James Time (hours)	Team Time (hours)	Location	Developer Name(s)	What was done?
01/28/2016	17:00	20:00	0	0	3	3	James House	James Vinson	Research Unity fileimport capability
5/2/2016	20:00	22:00	0	0	2	2	James House	James Vinson	Research Unity fileimport capability
5/2/2016	06:00	07:00	1	0	0	1	Funk House	William Funk	Purchase of Oculus Dev Kit 2 on eBay
8/2/2016	18:30	22:30	4	4	4	4	HEC 102	William Funk, Jorge Rodriguez, James Vinson	Requirements Plan
9/2/2016	17:00	18:00	0	0	1	1	HEC 102	James Vinson	Research Unity node editor
11/2/2016	14:45	15:00	0	0.25	0	0.25	BA 114	Jorge Rodriguez	Meeting w/ Lienecker ( Email retrieval )
02/13/2016	10:00	21:00	11	0	0	11	O'Leno Park	William Funk	Github, Slack, Waffle creation and integration. Include sponsor, and populate Waffle with issues
02/13/2016	21:00	00:00	0	3	0	3	Lake Claire	Jorge Rodriguez	Unity Project (Learning)
02/14/2016	11:00	13:30	0	2.5	0	3	Lake Claire	Jorge Rodriguez	Unity Project (Learning)
02/14/2016	11:30	16:30	5	0	0	5	On the road	William Funk	Concept of Operations Document
02/14/2016	23:30	24:00:00	0.5	0	0	0.5	Funk House	William Funk	Concept of Operations Document
02/15/2016	00:00	01:15	1.25	0	0	1.25	Funk House	William Funk	Concept of Operations Document
02/15/2016	11:30	13:00	0	1.5	0	3	Lake Claire	Jorge Rodriguez	Unity Project (Learning)
02/15/2016	13:30	14:00	0	0	0.5	0.5	Lienecker Office	James Vinson	Light Update of the Project
02/15/2016	15:00	16:30	1.5	0	0	1.5	UCF Library	William Funk	Concept of Operations Document
02/15/2016	18:00	20:00	2	2	2	2	UCF Library	William Funk, Jorge Rodriguez, James Vinson	Git tutorial / Assigned demo Unity projects
02/15/2016	23:00	01:00:00	0	0	2	2	James Apart	James Vinson	Vr Gui Manipulation Demo (Google CardBoard)
02/16/2016	11:00	14:30	0	0	3.5	3.5	Senior DLab	James Vinson	Researching function graphs
02/16/2016	11:30	13:00	0	1.5	0	3	Lake Claire	Jorge Rodriguez	Unity Project (Learning)
02/16/2016	17:00	19:00	0	0	2	2	Senior DLab	James Vinson	Researching function graphs
02/17/2016	11:30	13:00	0	1.5	0	3	Lake Claire	Jorge Rodriguez	Unity Project (Learning)
02/17/2016	15:00	16:30	1.5	1.5	1.5	1.5	Leinecker's Office	William Funk, Jorge Rodriguez, James Vinson	Sponsor meeting to discuss sponsor's expectations / group test of Oculus DK2
02/18/2016	11:00	12:30	1.5	0	0	1.5	UCF Library	William Funk	Research and purchase of the Leap Motion Control
02/18/2016	11:30	13:00	0	1.5	0	3	Lake Claire	Jorge Rodriguez	Unity Project (Learning)
02/20/2016	09:45	10:30	0.75	0	0	0.75	Funk House	William Funk	Updating and implementing better hour tracking in time log / added expense sheet / Journal entry
02/20/2016	20:00	00:30	4.5	4.5	4.5	4.5	Funk House	William Funk, Jorge Rodriguez, James Vinson	Block Diagrams for Project Proposal
02/21/2016	16:00	19:00	0	3	0	3	Lake Claire	Jorge Rodriguez	Unity Project (Learning - Raycasting)
02/22/2016	05:00	06:30	1.5	0	0	1.5	Funk House	William Funk	Block Diagrams for Project Proposal
02/22/2016	08:00	09:00	1	0	0	1	Library	William Funk	Block Diagrams for Project Proposal
02/22/2016	11:00	11:30	0.5	0	0	0.5	Library	William Funk	Block Diagrams for Project Proposal
02/22/2016	13:45	14:30	0.75	0	0	0.75	CB-204	William Funk	Block Diagrams for Project Proposal
02/22/2016	14:45	16:45	2	2	2	2	Senior DLab	William Funk, Jorge Rodriguez, James Vinson	Scheduling/Time Estimates for Project Proposal
02/22/2016	17:00	21:00	4	0	0	4	Senior DLab	William Funk	Scheduling/Time Estimates for Project Proposal
02/22/2016	20:00	21:30	0	0	1.5	1.5	James apartment	James Vinson	Developer Blog, development
02/22/2016	21:00	23:00	2	0	0	2	Senior DLab	William Funk	Project Proposal Writeup
02/23/2016	06:00	08:15	2.25	0	0	2.25	Funk House	William Funk	Milestones/Scheduling section of Project Proposal Document
02/23/2016	15:00	17:45	2.75	0	0	2.75	HPA-1	William Funk	Milestones/Scheduling section of Project Proposal Document
02/23/2016	17:00	17:30	0	0	0.5	0.5	Senior DLab	James Vinson	Project Proposal Writeup: Personal Motivation

## Expenses
		578
EXPENSE LOG

Date	Item/Service	Cost ($)	Who Contributed
4/2/2016	Oculus Development Kit 2.0	550	Sponsor (leinecker) = $400 / William Funk = $50 / Jorge Rodriguez = $50 / James Vinson = $50
02/18/2016	Leap Motion Controller	28	William Funk = $28

## Time Estimate
	Node	Estimated Days (8 Hours)	# of Developers	Total
RESEARCH	Learn C# For Unity and Unity	1	3	3
	Learn Visual Studios	1	3	3
	Unity Customization	2	2	4
	Unit Tests	2	3	6
	3D Math & 3D Graphics	1	3	3
	Parsers & Transpilers	2	3	6
	Visual Parsers & Visual Transpiler	1	3	3
	UX Design (3D Environment)	1	3	3
	Visual Programming Languages	2	3	6	14
	Oculus & Leap & Myo	1	3	3	40
DESIGN	Activity & UML & Sequence Diagrams	2	3	6
	Modular Function Graphs	1	3	3
	Parser SQL	1	3	3
	Parser C#	1	3	3
	Transpiler SQL	1	3	3
	Transpiler C#	1	3	3
	Concept Art	2	1	2
	Visual Design & Workflow	2	3	6
	Target Audience & User Personas + Wire Frame + Wireframe	1	1	1
	User Input Handling	1	3	3
	Documentation (Forms)	2	3	6
	Logger	1	3	3	18
	Unit Tests	2	3	6	48
IMPLEMENTATION --- DATABASE & WEBSITE	Parser SQL + Scanner SQL	2	1	2	Funk
	Transpiler SQL	7	1	7	Funk
	3D Mesh Factory	3	1	3	Rodriguez
	Object Relationship Matrix	3	1	3	Rodriguez
	Parent/Child Adoption	3	1	3	Vinson
	Function Graph	4	1	4	Rodriguez
	Database Communication Layer	3	1	3	Funk
	Demo Database	0.5	1	0.5	Funk
	Session Storage Database	4	1	4	Vinson
	Logger	2	1	2	Vinson
	Application State Manager (Main Menu)	0.5	1	0.5	Vinson
	User Error Detection & Handling SQL	4	1	4	Rodriguez
	Landscape (View Mode)	1	1	1	Rodriguez
	Landscape (Edit Mode)	3	1	3	Rodriguez
	UI Database (View Mode)	7	1	7	Vinson
	UI Database (Edit Mode)	10	1	10	Vinson
	Position Management System SQL	7	1	7	Funk	Rodriguez
	HTML/CSS Website	1	1	1	Funk
	JavaScript Website	1	1	1	Funk
	Backend Website	1	1	1	Funk
	Sound Resource	2	1	2	Rodriguez
	Sound Cue Implement	2	1	2	Rodriguez
	Visual Cue Resources	2	1	2	Funk
	Visual Cue Implement	2	1	2	Funk
	Keyboard/Mouse Handler	1	1	1	Vinson
IMPLEMENTATION --- C# & WEBSITE	Parser C# + Scanner C# (Input)	21	1	21	Vinson
	Transpiler C# (Input)	21	1	21	Funk
	Parser C# + Scanner C# (Output)	21	1	21	Funk
	3D Mesh Factory C#	7	1	7	Rodriguez
	Object Relationship Matrix C#	14	1	14	Rodriguez
	Parent/Child Adoption C#	7	1	22	Vinson
	Function Graph	14	1	14	Rodriguez
	Demo C# Project	3	1	3	Funk
	Session Storage C#	10	1	10	Vinson
	Logger C#	7	1	7	Vinson
	Application State Manager (Main Menu) C#	1	1	1	Vinson
	User Error Detection & Handling C#	10	1	10	Rodriguez
	UI C# (View Mode)	7	1	7	Vinson
	UI C# (Edit Mode)	7	1	7	Vinson
	Position Managements System C#	3	1	3	Funk	Rodriguez
	Keyboard/Mouse Handler	1	1	1	Vinson
	Leap Handler	7	1	7	Funk
	Sound Resource C#	2	1	2	Rodriguez
	Sound Cue Implement C#	2	1	2	Rodriguez
	Visual Cue Resources C#	2	1	2	Funk
	Visual Cue Implement C#	2	1	2	Funk
	Montage	2	1	2	Rodriguez
	Database Demo	1	1	1	Rodriguez
	C# Demo	1	1	1	Rodriguez
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0