## TimeLog
			40	28.5	27.75	75.25
TIME LOG

Date	Time Start	Time End	Funk Time (hours)	Jorge Time (hours)	James Time (hours)	Team Time (hours)	Location	Developer Name(s)	What was done?
01/28/2016	17:00	20:00	0	0	3	3	James House	James Vinson	Research Unity fileimport capability
5/2/2016	20:00	22:00	0	0	2	2	James House	James Vinson	Research Unity fileimport capability
5/2/2016	06:00	07:00	1	0	0	1	Funk House	William Funk	Purchase of Oculus Dev Kit 2 on eBay
8/2/2016	18:30	22:30	4	4	4	4	HEC 102	William Funk, Jorge Rodriguez, James Vinson	Requirements Plan
9/2/2016	17:00	18:00	0	0	1	1	HEC 102	James Vinson	Research Unity node editor
11/2/2016	14:45	15:00	0	0.25	0	0.25	BA 114	Jorge Rodriguez	Meeting w/ Lienecker ( Email retrieval )
02/13/2016	10:00	21:00	11	0	0	11	O'Leno Park	William Funk	Github, Slack, Waffle creation and integration. Include sponsor, and populate Waffle with issues
02/13/2016	21:00	00:00	0	3	0	3	Lake Claire	Jorge Rodriguez	Unity Project (Learning)
02/14/2016	11:00	13:30	0	2.5	0	3	Lake Claire	Jorge Rodriguez	Unity Project (Learning)
02/14/2016	11:30	16:30	5	0	0	5	On the road	William Funk	Concept of Operations Document
02/14/2016	23:30	24:00:00	0.5	0	0	0.5	Funk House	William Funk	Concept of Operations Document
02/15/2016	00:00	01:15	1.25	0	0	1.25	Funk House	William Funk	Concept of Operations Document
02/15/2016	11:30	13:00	0	1.5	0	3	Lake Claire	Jorge Rodriguez	Unity Project (Learning)
02/15/2016	13:30	14:00	0	0	0.5	0.5	Lienecker Office	James Vinson	Light Update of the Project
02/15/2016	15:00	16:30	1.5	0	0	1.5	UCF Library	William Funk	Concept of Operations Document
02/15/2016	18:00	20:00	2	2	2	2	UCF Library	William Funk, Jorge Rodriguez, James Vinson	Git tutorial / Assigned demo Unity projects
02/15/2016	23:00	01:00:00	0	0	2	2	James Apart	James Vinson	Vr Gui Manipulation Demo (Google CardBoard)
02/16/2016	11:00	14:30	0	0	3.5	3.5	Senior DLab	James Vinson	Researching function graphs
02/16/2016	11:30	13:00	0	1.5	0	3	Lake Claire	Jorge Rodriguez	Unity Project (Learning)
02/16/2016	17:00	19:00	0	0	2	2	Senior DLab	James Vinson	Researching function graphs
02/17/2016	11:30	13:00	0	1.5	0	3	Lake Claire	Jorge Rodriguez	Unity Project (Learning)
02/17/2016	15:00	16:30	1.5	1.5	1.5	1.5	Leinecker's Office	William Funk, Jorge Rodriguez, James Vinson	Sponsor meeting to discuss sponsor's expectations / group test of Oculus DK2
02/18/2016	11:00	12:30	1.5	0	0	1.5	UCF Library	William Funk	Research and purchase of the Leap Motion Control
02/18/2016	11:30	13:00	0	1.5	0	3	Lake Claire	Jorge Rodriguez	Unity Project (Learning)
02/20/2016	09:45	10:30	0.75	0	0	0.75	Funk House	William Funk	Updating and implementing better hour tracking in time log / added expense sheet / Journal entry
02/20/2016	20:00	00:30	4.5	4.5	4.5	4.5	Funk House	William Funk, Jorge Rodriguez, James Vinson	Block Diagrams for Project Proposal
02/21/2016	16:00	19:00	0	3	0	3	Lake Claire	Jorge Rodriguez	Unity Project (Learning - Raycasting)
02/22/2016	05:00	06:30	1.5	0	0	1.5	Funk House	William Funk	Block Diagrams for Project Proposal
02/22/2016	08:00	09:00	1	0	0	1	Library	William Funk	Block Diagrams for Project Proposal
02/22/2016	11:00	11:30	0.5	0	0	0.5	Library	William Funk	Block Diagrams for Project Proposal
02/22/2016	13:45	14:30	0.75	0	0	0.75	CB-204	William Funk	Block Diagrams for Project Proposal
02/22/2016	14:45	16:30	1.75	1.75	1.75	1.75	Senior DLab	William Funk, Jorge Rodriguez, James Vinson	Scheduling/Time Estimates for Project Proposal

## Expenses
		578
EXPENSE LOG

Date	Item/Service	Cost ($)	Who Contributed
4/2/2016	Oculus Development Kit 2.0	550	Sponsor (leinecker) = $400 / William Funk = $50 / Jorge Rodriguez = $50 / James Vinson = $50
02/18/2016	Leap Motion Controller	28	William Funk = $28

## Time Estimate
	Node	Estimated Days (8 Hours)	# of Developers	Total
RESEARCH	Learn C# For Unity and Unity	1	3	3
	Learn Visual Studios	1	3	3
	Unity Customization	2	2	4
	Unit Tests	2	3	6
	3D Math & 3D Graphics	1	3	3
	Parsers & Transpilers	2	3	6
	Visual Parsers & Visual Transpiler	1	3	3
	UX Design (3D Environment)	1	3	3
	Visual Programming Languages	2	3	6	14
	Oculus & Leap & Myo	1	3	3	40
DESIGN	Activity & UML & Sequence Diagrams	1	3	3
	Modular Function Graphs	1	3	3
	Parser SQL	1	3	3
	Parser C#	1	3	3
	Transpiler SQL	1	3	3
	Transpiler C#	1	3	3
	Concept Art	2	1	2
	Visual Design & Workflow	2	3	6	*
	Target Audience & User Personas + Wire Frame + Wireframe	1	1	1
	User Input Handling	1	3	3
	Documentation (Forms)	2	3	6
	Logger	1	3	3	17
	Unit Tests	2	3	6	45
IMPLEMENTATION --- DATABASE & WEBSITE	Parser SQL + Scanner SQL	2	1	2
	Transpiler SQL	7	1	7
	3D Mesh Factory	3	1	3
	Object Relationship Matrix	3	1	3
	Parent/Child Adoption	3	1	3
	Database Communication Layer	3	1	3
	Demo Database	0.5	1	0.5
	Session Storage Database	4	1	4
	Logger	2	1	2	*
	Application State Manager (Main Menu)	0.5	1	0.5
	User Error Detection & Handling SQL	4	1	4
	Landscape (View Mode)	1	1	1
	Landscape (Edit Mode)	3	1	3
	UI Database (View Mode)	7	1	7
	UI Database (Edit Mode)	10	1	10
	Position Managements System SQL	7	1	7
	HTML/CSS Website	1	1	1
	JavaScript Website	1	1	1
	Backend Website	1	1	1
	Sound Resource	2	1	2
	Sound Cue Implement	2	1	2
	Visual Cue Resources	2	1	2
	Visual Cue Implement	2	1	2	72
	Keyboard/Mouse Handler	1	1	1	72	24	192
IMPLEMENTATION --- C# & WEBSITE	Parser C# + Scanner C# (Input)	21	1	21
	Parser C# + Scanner C# (Output)	21	1	21
	3D Mesh Factory C#	7	1	7
	Object Relationship Matrix C#	14	1	14
	Parent/Child Adoption C#	7	1	7
	Demo C# Project	3	1	3
	Session Storage C#	10	1	10
	Logger C#	7	1	7
	Application State Manager (Main Menu) C#	1	1	1
	User Error Detection & Handling C#	10	1	10
	UI C# (View Mode)	7	1	7
	UI C# (Edit Mode)	7	1	7
	Position Managements System C#	3	1	3
	Keyboard/Mouse Handler	1	1	1
	Leap Handler	7	1	7
	Sound Resource C#	2	1	2
	Sound Cue Implement C#	2	1	2
	Visual Cue Resources C#	2	1	2	134
	Visual Cue Implement C#	2	1	2	134	44.66666667	357.3333333
				0
				0
				0	223	74.33333333	594.6666667
				0		3.69955157
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0
				0